## 13 LAKH BBU
Annexure-I
Table: B-Transmission Line Work -Invoicing Purpose
| Line Cost / KM in INR | [8 empty] | 1300000
| Sl No | Item Description | Percentage (%) | Quantity | Unit | Unit Price | Total Price | GST | GST value | Total Price (Incl GST)
a. Delivery of 100% of transmission line & S/S bay material (poles, conductor, insulators etc.)
| 1 | Transmission Line Route and Right of Way (ROW) Survey | 5% | 1 | KM | 65000 | 65000 | 18% | 11700 | 76700 | Service
| 2 | Design engineering & approval of all major drawings | 5% | 1 | KM | 65000 | 65000 | 18% | 11700 | 76700 | Service
S | 3 | Transmission Tower/Poles | 10% | 1 | KM | 130000 | 130000 | 18% | 23400 | 153400 | Material
S | 4 | Conductors, Insulators, Cross arms and Braces Earthing, Material and Connectors, etc. | 10% | 1 | KM | 130000 | 130000 | 18% | 23400 | 153400 | Material
|  |  | 30% |  |  | Total Value | 390000 |  | 70200 | 460200
b. On commissioning of 100% of transmission line & S/S bay material (poles, conductor, insulators etc.)
| 1 | Completion of Foundation works, etc | 15% | 1 | Km | 195000 | 195000 | 18% | 35100 | 230100 | Service
| 2 | Installation, Erection and interconnection of Transmission line (Underground/Overhead) | 15% | 1 | Km | 195000 | 195000 | 18% | 35100 | 230100 | Service
|  |  | 30% |  |  | Total Value | 390000 |  | 70200 | 460200
c. Transmission Line readiness to charge
| 1 | All required Approvals from CEIG / MSEDCL / MEDA / MAHAGENCO etc. | 15% | 1 | Lot | 195000 | 195000 | 18% | 35100 | 230100 | Service
| 2 | Testing and Commissioning | 25% | 1 | Km | 325000 | 325000 | 18% | 58500 | 383500 | Service
|  |  | 40% |  |  | Total Value | 520000 |  | 93600 | 613600
[6 empty] | Total Transmission Line work Value | 1300000 |  | 234000 | 1534000
| Note: | The total contract value stated in this BBU is final, and no additional payments will be made by the M/s. ORL for work performed under the contract's terms, conditions and scope of work.