## 60% & 40% 95 Cr VEL fix
Annexure-I
| Total Project Value in INR | [8 empty] | 47500000
Table: A- EPC Work -Invoicing Purpose
| Sl No | Item Description | Percentage (%) | Quantity | Unit | Unit Price | Total Price | GST | GST value | Total Price (Incl GST) |  |  | A |  | 60%
| a. Delivery of module mounting structure at site | [10 empty] | 60% | 54% | 0% | 40%
| 1 | Land Development Work-Topography Survey & Hydrology Survey & Soil Testing | 1% | 1 | Lot | 475000 | 475000 | 18% | 85500 | 560500 | Service
| 2 | Boundary Fencing | 3% | 1 | Lot | 1425000 | 1425000 | 18% | 256500 | 1681500 | Service
| 3 | Construction of Roads | 1.65% | 1 | Lot | 783750 | 783750 | 18% | 141075 | 924825 | Service
| 4 | Drainage System | 1% | 1 | Lot | 475000 | 475000 | 18% | 85500 | 560500 | Service
S | 5 | Module mounting structure | 21% | 1 | Lot | 9975000 | 9975000 | 18% | 1795500 | 11770500 | Material
|  |  | 27.65% |  |  | Total Value | 13133750 |  | 2364075 | 15497825
| b. On the erection of module mounting structure | [10 empty] | 40% | 46%
| 1 | Module Mounting Structures- Column Post | 6% | 1 | Lot | 275000 | 2850000 | 18% | 513000 | 3363000 | Service
| 2 | On the erection of Module Mounting Structures- Super Structure | 2% | 1 | Lot | 950000 | 950000 | 18% | 171000 | 1121000 | Service
|  |  | 8% |  |  | Total Value | 3800000 |  | 684000 | 4484000
c. Delivery of transformers at site including all accessories
S | 1 | Transformers at site including all accessories | 7% | 1 | Lot | 3325000 | 3325000 | 18% | 598500 | 3923500 | Material
|  |  | 7% |  |  | Total Value | 3325000 |  | 598500 | 3923500
d. On the erection of transformers at site including all accessories
| 1 | Erection of transformer at site including all accessories | 1% | 1 | Lot | 475000 | 475000 | 18% | 85500 | 560500 | Service
|  |  | 1% |  |  | Total Value | 475000 |  | 85500 | 560500
e. Delivery of LT & HT Panels at site including all accessories
S | 1 | LT Panels including all accessories | 4.5% | 1 | Lot | 2137500 | 2137500 | 18% | 384750 | 2522250 | Material
S | 2 | HT Panels including all accessories | 4.5% | 1 | Lot | 2137500 | 2137500 | 18% | 384750 | 2522250 | Material
|  |  | 9% |  |  | Total Value | 4275000 |  | 769500 | 5044500
f. On the erection of LT & HT Panels at site including all accessories
| 1 | LT Panels at site including all accessories | 1% | 1 | Lot | 475000 | 475000 | 18% | 85500 | 560500 | Service
| 2 | HT Panels at site including all accessories | 1% | 1 | Lot | 475000 | 475000 | 18% | 85500 | 560500 | Service
|  |  | 2% |  |  | Total Value | 950000 |  | 171000 | 1121000
g. Delivery of all cables (DC, AC LV, AC MV, Aux ) at site
S | 1 | DC Cable- from Module to Inv. (1C x 4/6 Sq. mm., CU cable) | 5% | 1 | Lot | 2375000 | 2375000 | 18% | 427500 | 2802500 | Material
S | 2 | LT AC Cable (1.9/3.3 kV, Aluminium, XLPE armoured) & Aux. Cables | 4% | 1 | Lot | 1900000 | 1900000 | 18% | 342000 | 2242000 | Material
S | 3 | AC HT Cable | 4% | 1 | Lot | 1900000 | 1900000 | 18% | 342000 | 2242000 | Material
|  |  | 13% |  |  | Total Value | 6175000 |  | 1111500 | 7286500
h. On laying of all cables (DC, AC LV, AC MV, Aux ) at site
| 1 | DC Cable- from Module to Inv. (1C x 4/6 Sq. mm., CU cable) | 1% | 1 | Lot | 475000 | 475000 | 18% | 85500 | 560500 | Service
| 2 | LT AC Cable (1.9/3.3 kV, Aluminium, XLPE armoured) & Aux. Cables | 1% | 1 | Lot | 475000 | 475000 | 18% | 85500 | 560500 | Service
| 3 | AC HT Cable | 1% | 1 | Lot | 475000 | 475000 | 18% | 85500 | 560500 | Service
|  |  | 3% |  |  | Total Value | 1425000 |  | 256500 | 1681500
i. Delivery of all Balance of material including evacuation arrangement at solar plant end
S | 1 | Supply of all Balance of material including evacuation arrangement at solar plant end | 10% | 1 | Lot | 4750000 | 4750000 | 18% | 855000 | 5605000 | Material
|  |  | 10% |  |  | Total Value | 4750000 |  | 855000 | 5605000
j. On the installation of all Balance of material including evacuation arrangement at solar plant end
| 1 | Installation of all Balance of material including evacuation arrangement of solar power plant | 2% | 1 | Lot | 950000 | 950000 | 18% | 171000 | 1121000 | Service
|  |  | 2% |  |  | Total Value | 950000 |  | 171000 | 1121000
k. Against all the Pre-commissioning approvals such as those from MEDA, MAHAGENCO, DISCOM, CEIG, etc. as applicable
| 1 | Against all the Pre-commissioning approvals such as those from MEDA, MAHAGENCO, DISCOM, CEIG, etc as applicable | 1.5% | 1 | Lot | 712500 | 712500 | 18% | 128250 | 840750 | Service
|  |  | 1.5% |  |  | Total Value | 712500 |  | 128250 | 840750
l. On 100% completion of electrical, mechanical and civil installation of plant
| 1 | Charging completion of electrical installation of plant - HOTO | 3% | 5 | MW | 285000 | 1425000 | 18% | 256500 | 1681500 | Service
| 2 | Charging completion of mechanical installation of plant - HOTO | 1% | 5 | MW | 95000 | 475000 | 18% | 85500 | 560500 | Service
| 3 | Charging completion of civil installation of plant - HOTO | 2% | 5 | MW | 190000 | 950000 | 18% | 171000 | 1121000 | Service
|  |  | 6% |  |  | Total Value | 2850000 |  | 513000 | 3363000
m. Bay readiness to charge
| 1 | Government Substation Bay | 3.85% | 1 | Lot | 1828750 | 1828750 | 18% | 329175 | 2157925 | Service
|  |  | 3.85% |  |  | Total Value | 1828750 |  | 329175 | 2157925
n. On commissioning of plant and injection into grid demonstrated at revenue metering
| 1 | Final commissioning of plant and injection into grid demonstrated at revenue metering | 2% | 5 | MW | 190000 | 950000 | 18% | 171000 | 1121000 | Service
|  |  | 2% |  |  | Total Value | 950000 |  | 171000 | 1121000
o. On successful completion of PG Test
| 1 | successful completion of PG Test | 2% | 5 | MW | 190000 | 950000 | 18% | 171000 | 1121000 | Service
|  |  | 2% |  |  | Total Value | 950000 |  | 171000 | 1121000
p. On final acceptance and handover
| 1 | Final acceptance and handover the plant (After Hand Over Take Over to our O&M Team at the time of commencement of O&M by Contractor) | 2% | 5 | MW | 190000 | 950000 | 18% | 171000 | 1121000 | Service
|  |  | 2% |  |  | Total Value | 950000 |  | 171000 | 1121000
[6 empty] | Total EPC Value | 47500000 |  | 8550000 | 56050000